## Sheet1
Project Phase | Start Date | End Date | Summary Notes
Step01-Scraping from Indeed Pages to build initial dataframe | 2018-06-30 | 2018-06-30 | Completed
Step02-Get Full JD | 2018-07-01 | 2018-07-01 | Completed
Step03-Countvectorizer_Regional-Technical_Requirements | 2018-07-02 | 2018-07-02 | Completed
Step04-StopWords_Regional_Cultural_Requirements | 2018-07-03 | 2018-07-04 | Completed
Step05-Stop Words-Regional_TechnicalRequirements | 2018-07-04 | 2018-07-04 | Completed
Step06-Cleaning-BaselineResume | 2018-07-05 | 2018-07-05 | Completed
Step07-Countvectorize_Resume | 2018-07-06 | 2018-07-06 | Completed
Step08-Cleaning-Updated_Resume | 2018-07-07 | 2018-07-07 | Completed
Step09-Countvectorize_Updated_Resume | 2018-07-08 | 2018-07-08 | Completed
Step10-Capstone-Getting Individual JDs | 2018-07-09 | 2018-07-09 | Completed
Step11-Cleaning-Individual_JD | 2018-07-10 | 2018-07-12 | Completed
Step12-Using Cosine Similarity to compare documents | 2018-07-10 | 2018-07-11 | Completed
Step13-UsingGMaps | 2018-07-11 | 2018-07-12 | Completed
Step14-Report Writeup + Technical Analysis | 2018-07-12 | 2018-07-13
Step15-Create Presentations | 2018-07-13 | 2018-07-13